## Summary
1. Project summary: 1,1 Currently implementing 4 web projects: - ATS: FA step/units status tracking - BTS: Burn in time/test result track - UTS: Online Unit load status report - CTB; lMaterial distribution tracking 1.2 Work process: - Confirm with VN-IT & LH mentor about the physical configuration (Done) --> DRI: EPM Thomas - Deploy CTB on Local(MacOS) success (Done) - Deploy ATS, BTS, UST on Local (Win10) success (Done) - SOP docment training deploy ATS, BTS, UTS, CTB on Local (VN) (Done) - Keep folow English translate task of LH mentor (Done) - Learn about CTB structure (Done) - Align with LH mentor about port number to deploy web service (Done) - Collect VN NPI PC's IP to open firewall (Done) --> DRI: EPM Tony/Nick - Contact IT create account SSH access log on Server (Done) - Install & Config MySQL on Server Centos7 (10.221.132.30) & import data test (Done) - Deploy ATS, BTS, UTS on Window Server : Install Appserv on window server: + Php 5x (done) + Mysql 5x (done) + Apache Web Server Version 2.2.8 (done) Config MySQL & connect to server 10.221.132.30 get data (done) Run success on address: 10.221.132.33/vn_ats, 10.221.132.33/vn_bts, 10.221.132.33/vn_uts, (done) - Training newbie deploy & hosting CTB on local (Done) - SOP deploy & hosting on local (Done) - Deploy CTB on Server: + Install python3.8 (Done) + Move source code from local to server (Done) + Move packages to server (gunicorn, nginx,virtaulenv, lib…) (on-going) -->DRI: Eden + Config and mix packages install runing (on-going) -->DRI: Eden - Contact LH research & traking use API SFC replace Oracle (On-going)-> DRI: Eden - CD website transfer: + ATS: - Research about ATS (On-going) --> DRI: Dustin - Install & Deploy ATS on Local(On-going) --> DRI: Dustin - Make SOP ATS (on-going) -->DRI: Dustin + NPI Academy: - Research about NPI Academy(On-going) --> DRI: Frenkie - Install & Deploy NPI Academy on Local(On-going) --> DRI: Frenkie - Make SOP NPI Academy(on-going) -->DRI: Frenkie - SW Training: + Make traning plan (Done) -->DRI: Zed + Training about structure Django P1 (Done) --> DRI: Eden 1.3 Expected OK2use: Jul-15
No | Item | Detail
1 | Timeline!A1
2 | Physical Configuration'!A1
3 | Web server deployport'!A1
4 | Setup Diagram'!A1
5 | NPI PC IP'!A1
6 | Web Deployed'!A1
7 | Training Plan'!A1
8 | LH Web Schedule'!A1

## Timeline
VN NPI WEB SERVICE
Close
On-going
Pending
[6 empty] | April |  |  |  | May |  |  |  | Jun |  |  |  | Jul
| MODULE | SYSTEM | TASK | DRI | CP | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | … | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | … | Remark
| BIG Data | Deploy on Local |  | Eden | 2024-05-15
|  | CTB | Research source code, use framework language | Eden | 2024-05-15 | [16 empty] | - SOP docment training deploy local (VN) (Done) - Deploy CTB on Local(MacOS) success (Done) - Keep folow English translate task of LH mentor (On-going) - Learn about CTB structure (On-going) | bar: April Week1
|  |  | Prepare to install tools (Install Git, Install Pycharm) | Eden | 2024-05-15 | bar: April Week1
|  |  | Learn Python 3.8, Django 2.1 | Eden | 2024-05-15 | bar: April Week1
|  |  | Install python 3.8, pyenv (virtual host), install pip | Eden | 2024-05-15 | bar: April Week1
|  |  | Learn about CTB structure | Eden | 2024-05-15 | bar: April Week1
|  |  | - Setting config Mysql, Oracel | Eden | 2024-05-15 | bar: April Week2
|  |  | - List app in CTB | Eden | 2024-05-15
|  |  | - Url, View, Models, Migration | Eden | 2024-05-15 | bar: April Week2 to April Week4
|  |  | Deploy and fixbug running on Local (MacOS) | Eden | 2024-05-15 | bar: April Week2 to April Week3
|  |  | Learn about multiple langue django | Eden | 2024-05-15 | bar: April Week3 to April Week4
|  |  | Learn how to get system data | Eden | 2024-05-15 | bar: April Week3
|  |  | Learn how to use the system | Eden | 2024-05-15
|  |  | SOP docment training deploy local | Eden | 2024-05-15 | bar: April Week2
|  | ATS | Research source code | Eden | 2024-05-15 | [16 empty] | - Deploy ATS on Local(Win10) success (Done) | bar: April Week2
|  |  | Learn PHP5x, Mysql5x, Apache | Eden | 2024-05-15 | bar: April Week2
|  |  | Appserv download & install & setting on Win10 | Eden | 2024-05-15 | bar: April Week2
|  |  | Clone and install studyPHP | Eden | 2024-05-15 | bar: April Week2
|  |  | - Setting PHP version | Eden | 2024-05-15 | bar: April Week2
|  |  | - Config Apache | Eden | 2024-05-15 | bar: April Week2
|  |  | - Config Mysql | Eden | 2024-05-15 | bar: April Week2
|  |  | Deploy and fixbug running Local Win10 | Eden | 2024-05-15 | bar: April Week2
|  | BTS | Config Mysql | Eden | 2024-05-15 | [16 empty] | - Deploy BTS on Local(Win10) success (Done) | bar: April Week2
|  |  | Deploy and fixbug running Local Win10 | Eden | 2024-05-15 | bar: April Week2 to April Week3
|  |  | Learn how to get system data | Eden | 2024-05-15 | bar: April Week3 to April Week4
|  |  | Learn how to use the system | Eden | 2024-05-15 | bar: April Week3 to April Week4
|  |  | SOP docment training deploy local | Eden | 2024-05-15 | bar: April Week2
|  | UTS | Config Mysql | Eden | 2024-05-15 | [16 empty] | - Deploy UST on Local(Win10) success (Done) - Training newbie deploy & hosting CTB on local (Done) - SOP deploy & hosting on local (Done) | bar: April Week2
|  |  | Deploy and fixbug running Local Win10 | Eden | 2024-05-15 | bar: April Week2 to April Week3
|  |  | Learn how to get system data | Eden | 2024-05-15 | bar: April Week3 to April Week4
|  |  | Learn how to use the system | Eden | 2024-05-15 | bar: April Week3 to April Week4
|  |  | SOP docment training deploy & hosting local (gunicorn + nginx) | Frenkie | 2024-05-15 | bar: April Week4 to May Week1
|  | Deploy on Server |  | Eden/Thomas/Carl | 2024-07-15
|  | Prepare Server | Contact with LH about server design (3 Centos servers, 1 window server) | Eden/Thomas | 2024-07-15 | [16 empty] | Contact with LH about server design (3 Centos servers, 1 window server) (done) | bar: April Week3
|  |  | Contact IT support setting firewall, public port | Eden/Thomas | 2024-07-15 | [16 empty] | - Align with LH mentor about port number to deploy web service (On-going) - Contact IT open firewall & port access server: + Internet access (done) + SSH access (3 server centos 7) (done) + Remote Destop Connection access (Window server) (done) - Contact IT LH create account SSH access to 4 servers | bar: April Week3 to April Week4
|  |  | Setting MySQL database on server Centos 7 | [18 empty] | - Install & config MySQL 5x on Server Centos 7 (10.221.132.30) (done) | bar: April Week3 to April Week4
|  |  | Setting backup database on server Centos 7 | Eden/Thomas | 2024-07-15 | [16 empty] | - Prepare setting environment (Done) - Contact LH confirm about backup database (on-going) | bar: April Week4 to May Week2
|  | CTB | Prepare install on Centos 7 | Eden/Carl | 2024-07-15 | [16 empty] | - Install python3.8 (Dome) - Move source code from local to server(Done) - Move packages to server (gunicorn, nginx,virtaulenv, lib…)(on-going) - Config and mix packages install runing (on-going) | bar: April Week4 to May Week2
|  |  | - Install python 3.8, pip, virtualenv | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week2
|  |  | - Install and Setting Mysql | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week2
|  |  | - Download & Install Gunicorn | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week2
|  |  | - Download & Install Nginx | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week2
|  |  | Config connect Mysql, Oracle | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week2
|  |  | Setting job, backup data | Eden/Carl | 2024-07-15
|  | ATS | Deploy on window server | Eden/Carl | 2024-07-15 | [16 empty] | - Install Appserv on window server: + php 5x (done) + Mysql 5x (done) + Apache Web Server Version 2.2.8 (done) - Config MySQL & connect to server 10.221.132.30 get data (done) - Run success on address: 10.221.132.33/vn_ats (done) - Install & config Oracle (reject) - Reseacrh and traking LH use SFC replace oracle (On-going) | bar: April Week3 to April Week4
|  |  | Dowload & install Appserv | Eden/Carl | 2024-07-15 | bar: April Week4
|  |  | Dowload & install oracle client, config connection | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week1
|  |  | Config connect Mysql | Eden/Carl | 2024-07-15 | bar: April Week4
|  |  | Config Apache, php.ini | Eden/Carl | 2024-07-15 | bar: April Week4
|  | BTS | Deploy on window server | Eden/Carl | 2024-07-15 | [16 empty] | - Install Appserv on window server: + php 5x (done) + Mysql 5x (done) + Apache Web Server Version 2.2.8 (done) - Config MySQL & connect to server 10.221.132.30 get data (done) - Run success on address: 10.221.132.33/vn_bts (done) -Reseacrh and traking LH use SFC replace oracle (On-going) | bar: April Week3 to April Week4
|  |  | Dowload & install Appserv | Eden/Carl | 2024-07-15 | bar: April Week4
|  |  | Dowload & install oracle client | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week1
|  |  | Config connect Mysql, Oracle | Eden/Carl | 2024-07-15 | bar: April Week4
|  |  | Config Apache, php.ini | Eden/Carl | 2024-07-15 | bar: April Week4
|  | UTS | Deploy on window server | Eden/Carl | 2024-07-15 | [16 empty] | - Install Appserv on window server: + php 5x (done) + Mysql 5x (done) + Apache Web Server Version 2.2.8 (done) - Config MySQL & connect to server 10.221.132.30 get data (done) - Run success on address: 10.221.132.33/vn_uts (done) - Install & config Oracle (reject) - Reseacrh and traking LH use SFC replace oracle (On-going) | bar: April Week3 to April Week4
|  |  | Dowload & install Appserv | Eden/Carl | 2024-07-15 | bar: April Week4
|  |  | Dowload & install oracle client | Eden/Carl | 2024-07-15 | bar: April Week4 to May Week1
|  |  | Config connect Mysql, Oracle | Eden/Carl | 2024-07-15 | bar: April Week4
|  |  | Config Apache, php.ini | Eden/Carl | 2024-07-15 | bar: April Week4

## Training Plan
SW Training Plan
|  |  | Common |  |  | Diags |  |  | SW-QT |  |  | BigData |  |  | Summary&Report
|  |  | Open |  | On-going |  | Close
No | Item | Document name | Week 1 | [6 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 |  | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34
1 | Macbook product | bar: Week 1 Day 1; Week 1 Day 6
2 | iPad product | J407 block diagram and components introduction.pptx | bar: Week 1 Day 2; Week 1 Day 6
3 | NPI Introduction | NPI Build_v2.0.pdf | bar: Week 1 Day 3; Week 1 Day 6
4 |  | NPI Build_Detail.pdf | bar: Week 1 Day 4; Week 1 Day 6
5 |  | NPI Ogz | bar: Week 1 Day 5 to Week 1 Day 6
6 | SMT Introduction | SMT Introduction_v2.0.pdf
7 | FATP Introduction | FATP Test Station Introduction.pdf
8 | Test Flow | J607 Test Flow V0.18.pdf
9 | Common tools | Insight.pdf
10 |  | Radar.pdf
11 |  | SFC.pdf
12 | GroundHog | GHLS and GHDS introduction-20190627.docx
13 | Product Mode | MacBook Mode Transfer.pdf
14 | Diags | Diag Validation and Testing.pptx
15 | SW-QT | Documentation (Introduct doccument to research)
16 | Bigdata | SW Bigdata system list
17 |  | ATS&BTS&UTS_deploy_SOP_V1.0.0.md
18 |  | ATS introduction V5.pptx
19 |  | BTS SOPV1.0.docx
20 |  | CTB_env_sop_build_virtual_environment_SOP_V1.0.pdf
21 |  | UTS SOP en.docx
22 |  | Database_config.xlsx
23 |  | WAMP (StudyPHP, Appserv) Introdoction
24 |  | ATS introducton & SOP install
25 |  | MTS introducton & SOP install
26 |  | SWAT introducton & SOP install
26 |  | Academy introducton & SOP install

## NPI PC IP
Window Server | [6 empty] | Centos7
No | 源IP | 目的IP | Port |  |  | 說明 | No | 源IP | 目的IP | Port |  |  | 說明
|  |  | TCP | UDP | ICMP |  |  |  |  | TCP | UDP | ICMP
1 | 10.149.189.* | 10.221.132.33 | 80/3389/3306 |  | ICMP | 性能监控 | 1 | 10.149.189.* | 10.221.132.30 10.221.132.31 10.221.132.32 | 22/80/3306/8000 |  | ICMP | 性能监控
2 | 10.224.94.* |  | 80/3389/3306 |  | ICMP | 性能监控 | 2 | 10.224.94.* |  | 22/80/3306/8000 |  | ICMP | 性能监控
3 | 10.221.157.67 |  | 80/3389/3306 |  | ICMP | 性能监控 | 3 | 10.221.157.67 |  | 22/80/3306/8000 |  | ICMP | 性能监控
4 | 10.221.156.138 |  | 80/3389/3306 |  | ICMP | 性能监控 | 4 | 10.221.156.138 |  | 22/80/3306/8000 |  | ICMP | 性能监控
5 | 10.221.158.106 |  | 80/3389/3306 |  | ICMP | 性能监控 | 5 | 10.221.158.106 |  | 22/80/3306/8000 |  | ICMP | 性能监控
6 | 10.221.157.233 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 6 | 10.221.157.233 |  | 80/3306/8000 |  | ICMP | Web系统使用
7 | 10.221.156.92 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 7 | 10.221.156.92 |  | 80/3306/8000 |  | ICMP | Web系统使用
8 | 10.221.156.159 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 8 | 10.221.156.159 |  | 80/3306/8000 |  | ICMP | Web系统使用
9 | 10.221.156.158 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 9 | 10.221.156.158 |  | 80/3306/8000 |  | ICMP | Web系统使用
10 | 10.221.158.179 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 10 | 10.221.158.179 |  | 80/3306/8000 |  | ICMP | Web系统使用
11 | 10.221.157.186 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 11 | 10.221.157.186 |  | 80/3306/8000 |  | ICMP | Web系统使用
12 | 10.221.157.123 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 12 | 10.221.157.123 |  | 80/3306/8000 |  | ICMP | Web系统使用
13 | 10.221.157.89 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 13 | 10.221.157.89 |  | 80/3306/8000 |  | ICMP | Web系统使用
14 | 10.221.156.172 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 14 | 10.221.156.172 |  | 80/3306/8000 |  | ICMP | Web系统使用
15 | 10.221.146.115 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 15 | 10.221.146.115 |  | 80/3306/8000 |  | ICMP | Web系统使用
16 | 10.221.157.108 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 16 | 10.221.157.108 |  | 80/3306/8000 |  | ICMP | Web系统使用
17 | 10.221.158.210 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 17 | 10.221.158.210 |  | 80/3306/8000 |  | ICMP | Web系统使用
18 | 10.221.132.30 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 18 | 10.221.132.30 |  | 80/3306/8000 |  | ICMP | Web系统使用
19 | 10.221.132.31 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 19 | 10.221.132.31 |  | 80/3306/8000 |  | ICMP | Web系统使用
20 | 10.221.132.32 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 20 | 10.221.132.32 |  | 80/3306/8000 |  | ICMP | Web系统使用
21 | 10.221.132.33 |  | 80/3389/3306 |  | ICMP | Web系统使用 | 21 | 10.221.132.33 |  | 80/3306/8000 |  | ICMP | Web系统使用

## List Web Deloyed
ATS | http://10.221.132.33/vn_ats
BTS | http://10.221.132.33/vn_bts
UTS | http://10.221.132.33/vn_uts